## Agenda
Agenda
Date |  |  | Time | Location
To Bring:
Items from previous meeting:
|  | Item |  |  | Responsible | Due
1
2
3
4
Items to discuss:
|  | Item |  |  | Responsible | Due
1
2
3
4
Additional notes:
Prepared by

## Minutes
Minutes
Participants |  | William, Jason, Liam, Khargan, Kylie |  | Date |  | 2018-07-30
|  | Items Delivered | Items Planned |  | Impediments
| William | Finalised team agreement, wrote out list of features from client perspective | Think of more features for the workshop |  | No
| Jason | Tried to think of more features | Improve features list |  | None
| Liam | Tried to think of more features | Try to think up more features |  | None
| Khargan | Created google drive for the team, put all features together for collaboration | Think up more features/ideas |  | Nothing
| Kylie | Created templates for meetings | Improve features list, agenda for next meeting |  | None
|  | Item Discussed | Resolution |  | Responsible |  | Due
| 1 | Team agreement | Everyone agreed that it was satisfactory; emailed to tutor |  | Will
| 2 | Client feature list | Will supplied his list and Khargan added it to the Google doc |  | Will, Khargan
| 3 | Feature list collaboration | Discussed what was needed for the next meeting; decided we should all read over our lists and think about options for discussion |  | All |  | 2018-08-01
Additional Notes:
Kylie promises to properly do agendas from now on
Prepared by |  | Kylie