## Agenda
Agenda
Date |  | 2018-08-05 | Time | 2pm | Location |  | Online
To Bring:
Items from previous meeting:
|  | Item |  |  |  | Responsible |  | Due
| 1 | Uploading last meeting's minutes |  |  |  | All
| 2 | Catch up on missed content - finalised feature list? |  |  |  | Kylie
| 3 | Catch up on missed content - user stories |  |  |  | Kylie
4
Items to discuss:
|  | Item |  |  |  | Responsible |  | Due
| 1 | Review existing user stories list - flesh out and refine |  |  |  | All |  | 2018-08-06
| 2 | Review development framework; discuss installations |  |  |  | All |  | 2018-08-06
| 3 | Jira discussion |  |  |  | All
4
Additional notes:
Prepared by |  | Kylie

## Minutes
Minutes
Participants |  | Kylie, Khargan, William, Jason, Liam |  | Date |  | 2018-08-05
|  | Items Delivered | Items Planned |  | Impediments
| William | I fleshed out my user stories | I don't think I have to do anything as of yet??? |  | lol, nothing's stopping me doing nothing
| Jason | Created some user stories | Merge/refine user stories so they aren't the same as everyone else's |  | None
| Liam | Made some user stories | Finish user stories |  | Nothing
| Khargan | Outlined some user stories for all situations (client, staff, manager etc) | Work on more user stories |  | nothing
| Kylie | I planned this meeting and tried to figure out some stuff about the user stories but I needed more info | I'm gonna do my user stories |  | Nope
|  | Item Discussed | Resolution |  | Responsible |  | Due
| 1 | User stories update | Kylie learned what was needed and agreed to contribute for next meeting; everyone will come together with stories next meeting |  | All
| 2 | Portfolios | William reminded everyone that portfolios exist; group reminder to save all individual work before collation, etc. |  | All
| 3 | Feature lists | Finalised list is unnecessary, because it gets turned into user lists |  | All
| 4 | Development framework | Discussed which languages everyone was comfortable with and how we could divide up the workload; will discuss further in later meetings |  | Kylie, Khargan, Jason, Liam
| 5 | Jira | Don't know; will ask her about it next workshop |  | All
| 6 | Individual repositories clarification | It's for the portfolios |  | All
7
8
9
10
Additional Notes:
Prepared by |  | Kylie