## Agenda
Agenda
Date |  | 2018-08-06 | Time | 12pm | Location |  | Online
To Bring:
Items from previous meeting:
|  | Item |  |  |  | Responsible |  | Due
| 1 | Share user stories |  |  |  | All
2
3
4
Items to discuss:
|  | Item |  |  |  | Responsible |  | Due
| 1 | Negotiate final list of user stories |  |  |  | All |  | 2018-08-08
| 2 | Check installations |  |  |  | All
3
4
Additional notes:
Prepared by |  | Kylie

## Minutes
Minutes
Participants |  | William, Jason, Liam, Khargan, Kylie |  | Date |  | 2018-08-06
|  | Items Delivered | Items Planned |  | Impediments
| William | I haven't done anything since the last meeting | I'm not sure what I have to get done by the next meeting |  | Nothing is stopping me
| Jason | Edited user stories | Refine user stories |  | Nothing
| Liam | Finished user stories | try to refine use stories |  | no
| Khargan | haven't really done anything, only really just looked at everyone elses user stories | Edit user stories |  | nothin
| Kylie | Planned meeting and did user stories | Maybe refine user stories? |  | None. I have a bus card now
|  | Item Discussed | Resolution |  | Responsible |  | Due
| 1 | Shared user stories | All added to one google doc |  | All
| 2 | Compilation of user stories | Will said he will go over the google doc and remove redundancies |  | Will
| 3 | Ensuring everyone has development tools installed | Everyone has it all installed |  | All |  | 2018-08-08
4
5
6
7
8
9
10
Additional Notes:
Prepared by |  | Kylie