## Agenda
Agenda
Date |  | 2018-08-08 | Time | 12pm | Location |  | Workshop
To Bring:
Items from previous meeting:
|  | Item |  |  |  | Responsible |  | Due
| 1 | Jira - ask tutor |  |  |  | All
| 2 | User stories update |  |  |  | Will
3
4
Items to discuss:
|  | Item |  |  |  | Responsible |  | Due
| 1 | How to run online meetings - time until start, expectations for speaking up |  |  |  | All
| 2 | Let people know where agendas will be available |  |  |  | Kylie
| 3 | Check that meeting dates/times are fine |  |  |  | All
4
Additional notes:
Prepared by |  | Kylie

## Minutes
Minutes
Participants |  | William, Jason, Liam, Khargan, Kylie |  | Date |  | 2018-08-08
|  | Items Delivered | Items Planned |  | Impediments
William
Jason
Liam
Khargan
Kylie
|  | Item Discussed | Resolution |  | Responsible |  | Due
| 1 | Jira | Not yet available; will keep asking at workshops
| 2 | User stories work | Went through each story and applied a priority according to Moscow model; will continue in next meeting |  | All |  | 2018-08-10
| 3 | Online meeting structure | Agreed to wait 15 min for late people |  | All
| 4 | Agenda availability | Let everyone know that agendas would be available ahead of time on git |  | Kylie
| 5 | Check that meeting dates/times are fine | Everyone is okay with them |  | All
| 6 | Some unable to do Sunday meeting | Rescheduled next meeting to Friday 12:30pm |  | All |  | 2018-08-10
| 7 | Khargan let us know that Bitbucket was not suitable | Moved over to Github; Khargan made a new repository |  | Khargan
8
9
10
Additional Notes:
Stand-ups were not performed because they were lost in the format of the workshop; Kylie will endeavour to make sure they are done in the future
Prepared by |  | Kylie