## Agenda
Agenda
Date |  | 2018-08-10 | Time | 12:30pm | Location |  | Online
To Bring:
Items from previous meeting:
|  | Item |  |  |  | Responsible |  | Due
| 1 | Finalise user stories backlog |  |  |  | All |  | 2018-08-10
| 2 | Organise planning poker |  |  |  | All |  | 2018-08-13
| 3 | Acceptance criteria |  |  |  | All
4
Items to discuss:
|  | Item |  |  |  | Responsible |  | Due
| 1 | User stories template - use ppt or Jira? |  |  |  | All
| 2 | Development of release and sprint plan |  |  |  | All
3
4
Additional notes:
Prepared by |  | Kylie

## Minutes
Minutes
Participants |  | Liam, Jason, William, Kylie |  | Date |  | 2018-08-10
|  | Items Delivered | Items Planned |  | Impediments
| William | Wrote out some acceptance criteria | Dunno yet |  | Nothing
| Jason | Installed Django, messed around with it | Keep messing with it/acceptance criteria |  | None
| Liam | Nothing | Work on acceptance criteria, mess with Django |  | none
Khargan
| Kylie | Planned this meeting, added previous minutes/agendas and templates to github | We'll see |  | None
|  | Item Discussed | Resolution |  | Responsible |  | Due
| 1 | User stories list | Will will combine stories that are too similar before next meeting
| 2 | User stories template | We would prefer to use Jira but we don't yet have access; we'll use the ppt style until we can transfer
| 3 | Planning poker | Kylie will draw up a template for a way to do this online |  | Kylie |  | 2018-08-13
| 4 | Acceptance criteria | Cannot be done until user stories are finalised; will organise next meeting
| 5 | Next meeting | Reminder that there will be no Sunday meeting; next will be Monday 12pm |  | All |  | 2018-08-13
6
7
8
9
10
Additional Notes:
Prepared by |  | Kylie