## Agenda
Agenda
Date |  | 2018-08-22 | Time | 12pm | Location |  | Workshop
To Bring:
Items from previous meeting:
|  | Item |  |  |  | Responsible |  | Due
| 1 | Finalise acceptance criteria |  |  |  | All
| 2 | Negotiate and finalise story points (poker) |  |  |  | All
3
4
Items to discuss:
|  | Item |  |  |  | Responsible |  | Due
1
2
3
4
Additional notes:
Prepared by |  | Kylie

## Minutes
Minutes
Participants |  | Liam, Will, Jason, Khargan, Kylie |  | Date |  | 2018-08-22
|  | Items Delivered | Items Planned |  | Impediments
| William | Acceptance criteria | Sprint plans |  | None
| Jason | Rango and acceptance criteria | Sprint plans |  | None
| Liam | Acceptance criteria | Sprint plans |  | Tiredness
| Khargan | Acceptance criteria | Sprint plans |  | None
| Kylie | Meeting plan, user stories/acceptance criteria | Not sure yet |  | None
|  | Item Discussed | Resolution |  | Responsible |  | Due
| 1 | User stories finalisation | Will took us through them and approved/whittled down as client |  | Will, all
| 2 | User stories INVEST check | Attempted as a group to make sure the user stories passed the INVEST test |  | All
| 3 | User stories perspective | Changed perspectives to those of client |  | All
| 4 | User stories specificity | Made user stories more specific and testable |  | All
| 5 | Marking criteria review | Went through marking criteria step by step to ensure we were on the right track |  | All
| 6 | Story points poker | Shared and discussed individual numbers; came to agreed numbers for each story |  | All
| 7 | User stories polish | Kylie will edit user stories to have a more consistent voice/better grammar |  | Kylie
| 8 | Sprint/release plan | To be started on before next meeting |  | All
9
10
Additional Notes:
Prepared by |  | Kylie