## Agenda
Agenda
Date |  | 2018-08-26 | Time | 2pm | Location |  | Online
To Bring:
Items from previous meeting:
|  | Item |  |  |  | Responsible |  | Due
| 1 | User stories polish |  |  |  | Kylie
| 2 | Release/sprint plan |  |  |  | All
3
4
Items to discuss:
|  | Item |  |  |  | Responsible |  | Due
1
2
3
4
Additional notes:
Prepared by |  | Kylie

## Minutes
Minutes
Participants |  | William, Jason, Liam, Khargan, Kylie |  | Date |  | 2018-08-26
|  | Items Delivered | Items Planned |  | Impediments
| William | Worked on the user stories and story points | Do a LOT more work on the user stories and story points |  | I might actually miss the monday and possibly the Wednesday workshop this week, but I'm not sure yet
| Jason | Created a new poker/user story points template for all to use | Try and start the hello world project for the workshop and help with the release and sprint planning |  | None
| Liam | Poker stuff, hello world stuff | More poker stuff |  | None
| Khargan | Started on release plan | Finish release / sprint plan |  | Mobile assignment due today but once that's done should be fine
| Kylie | Did a bit of work on the user stories, did a tiny bit of writing on the release plan | Will keep working on the release plan I guess? |  | General tiredness due to silly gaming tournament that I kept waking up at 3am for
|  | Item Discussed | Resolution |  | Responsible |  | Due
| 1 | Finalising user stories and story points | All done |  | All
| 2 | Release/sprint plan | Do for next meeting |  | All |  | 2018-08-27
| 3 | System roles - clarification | Do for next meeting |  | All |  | 2018-08-27
4
5
6
7
8
9
10
Additional Notes:
Will may not be available for next couple of meetings; will endeavour to let us know ahead of time
Prepared by |  | Kylie