## Agenda
Agenda
Date |  | 2018-08-27 | Time | 12pm | Location |  | Online
To Bring:
Items from previous meeting:
|  | Item |  |  |  | Responsible |  | Due
| 1 | Clarify what we want to achieve in the first sprint |  |  |  | All
| 2 | Release/sprint plan discussion
3
4
Items to discuss:
|  | Item |  |  |  | Responsible |  | Due
1
2
3
4
Additional notes:
Prepared by |  | Kylie

## Minutes
Minutes
Participants |  | Jason, Liam, Kylie |  | Date |  | 2018-08-27
|  | Items Delivered | Items Planned |  | Impediments
William
| Jason | Started on the Hello World project | Hopefully finish the project by tomorrow night |  | None
| Liam | Nothing really | Working on hello world stuff today |  | None
Khargan
| Kylie | Meeting plan, system roles, finalised user stories, first draft release plan, started on sprint plan | Finish up release/sprint plan, upload minutes from past meetings |  | None
|  | Item Discussed | Resolution |  | Responsible |  | Due
| 1 | Django update | Jason is pretty much on top of it; Liam will start working on it today |  | Jason, Liam
| 2 | Release plan scope | Current guesstimate is fine; if we aren't even close, it's a learning experience |  | All
| 3 | Finishing submission | Kylie will come up with rest of sprint plan; Jason will come up with estimates |  | Kylie, Jason
4
5
6
7
8
9
10
Additional Notes:
Liam has hit a busy period and will be unable to contribute to the user stories etc. before Wednesday
Prepared by |  | Kylie