## Agenda
Agenda
Date |  | 2018-09-03 | Time | 12pm | Location |  | Online
To Bring:
Items from previous meeting:
|  | Item |  |  |  | Responsible |  | Due
| 1 | Proper catchup on where we're at/what we're doing |  |  |  | All
2
3
4
Items to discuss:
|  | Item |  |  |  | Responsible |  | Due
1
2
3
4
Additional notes:
Prepared by |  | Kylie

## Minutes
Minutes
Participants |  | Liam, Kylie, Will, Jason, Khargan |  | Date |  | 2018-09-03
|  | Items Delivered | Items Planned |  | Impediments
| William | Not much | Not sure |  | Nothing
| Jason | Started looking indepth at Django app making | Keep working on Django stuff |  | None
| Liam | Nothing | Django stuff |  | Maths homework may inhibit my work
| Khargan | Looked into how the display of web apps actually work in django | probably start on the project itself? Idk |  | exam next week thats about it
| Kylie | Started learning how to do Django things | Keep learning Django things |  | None
|  | Item Discussed | Resolution |  | Responsible |  | Due
| 1 | Anything else to think about other than Django? | We looked at last week's workshop homework and decided to start focusing on delivering user stories for sprint 1 |  | Jason, Liam, Khargan, Kylie
2
3
4
5
6
7
8
9
10
Additional Notes:
Prepared by |  | Kylie