## Agenda
Agenda
Date |  | 2018-09-09 | Time | 2pm | Location |  | Online
To Bring:
Items from previous meeting:
|  | Item |  |  |  | Responsible |  | Due
| 1 | Touch base on sprint progress |  |  |  | All
2
3
4
Items to discuss:
|  | Item |  |  |  | Responsible |  | Due
| 1 | Discussion of specific user story allocations |  |  |  | All
2
3
4
Additional notes:
Prepared by |  | Kylie

## Minutes
Minutes
Participants |  | Will, Jason, Liam, Khargan, Kylie |  | Date |  | 2018-09-09
|  | Items Delivered | Items Planned |  | Impediments
| William | Creating component diagram/data flow diagram | Creating component diagram/data flow diagram |  | Nope
| Jason | Started on website | Continue working on website and hopefully make some more progress |  | Django is a bit hard to learn
| Liam | Starting on artefacts | Artefacts |  | None
| Khargan | Made generic home page sort of start on the website, created some tables in the database for things such as car, etc. | Fix up the home page so it actually looks presentable / add some CSS to all the templates for future use |  | Django being annoying
| Kylie | Got everything working from git, picked through the existing code to learn from it | Hopefully contribute something concrete |  | I have footy tickets this arvo and a dinner out tonight so will only have the morning to do stuff
|  | Item Discussed | Resolution |  | Responsible |  | Due
| 1 | List of pages for website | Will will determine based on user stories |  | Will
| 2 | Allocation of artefacts | Just do what we can for now - focus on back end |  | All
| 3 | Burndown chart | Will will update every Wednesday |  | Will, All
4
5
6
7
8
9
10
Additional Notes:
Prepared by |  | Kylie