## Agenda
Agenda
Date |  | 2018-09-16 | Time | 2pm | Location |  | Online
To Bring:
Items from previous meeting:
|  | Item |  |  |  | Responsible |  | Due
| 1 | Progress update |  |  |  | All
2
3
4
Items to discuss:
|  | Item |  |  |  | Responsible |  | Due
| 1 | Data flow and component diagrams |  |  |  | Will
2
3
4
Additional notes:
Prepared by |  | Kylie

## Minutes
Minutes
Participants |  | Liam, Will, Kylie, Khargan, Jason |  | Date |  | 2018-09-16
|  | Items Delivered | Items Planned |  | Impediments
| William | Web design for all the web pages, completed component diagram, completed data-flow diagram | Burndown chart and update sprint expectations?? |  | Tad sick also, should be ok by Wednesday
| Jason | Made one of the design slides for one of the webpages and already uploaded to github | Keep working on website |  | Artefacts lol
| Liam | Worked on account settings UI design | Account settings stuff |  | Work at Australian Tax Office
| Khargan | Made home page / template for the rest of the pages, made up a CSS sheet to made the page look good, as well as a couple different logos to test | Implement actual database to the site |  | Sickness that's about it
| Kylie | Started on the database | Working on the database |  | Still a bit unwell
|  | Item Discussed | Resolution |  | Responsible |  | Due
| 1 | Progress check | Everyone seems to feel okay |  | All
| 2 | Home page progress | Khargan supplied a screenshot for approval; pushed it to git |  | Khargan
| 3 | Database progress | Kylie is making good progress; currently trying to figure out if there is a way to automate reading csvs |  | Kylie
| 4 | Car pics | We will use one placeholder image as proof of concept |  | All
| 5 | Car recommendations | Discussed ideas of how to implement |  | All
| 6 | Burndown chart | Will asked for updates re. what stories are completed |  | Will
| 7 | Due date? | We will ask the tutor for clarification on Wednesday's meeting |  | All
8
9
10
Additional Notes:
Liam will not be available for Wednesday meetings for the next four weeks due to ATO commitments.
Prepared by |  | Kylie