## Agenda
Agenda
Date |  | 2018-09-19 | Time | 12pm | Location |  | Workshop
To Bring:
Items from previous meeting:
|  | Item |  |  |  | Responsible |  | Due
| 1 | Progress check-in |  |  |  | All
| 2 | Artefact review |  |  |  | All
3
4
Items to discuss:
|  | Item |  |  |  | Responsible |  | Due
| 1 | Class diagram |  |  |  | All
2
3
4
Additional notes:
Prepared by |  | Kylie

## Minutes
Minutes
Participants |  | William, Khargan, Jason, Kylie |  | Date |  | 2018-09-19
|  | Items Delivered | Items Planned |  | Impediments
| William | Nothing (all done) | Refine/rearrange sprint plan |  | Another subject has assessment due
| Jason | Made reporting form | Class diagram, maybe another page |  | None
Liam
| Khargan | Made sorting javascript code for table | Login page |  | None
| Kylie | Database | Fix up database, create artefacts |  | Assessment due in two days
|  | Item Discussed | Resolution |  | Responsible |  | Due
| 1 | Reviewed delivered artefacts with tutor | Kylie and Liam to make 4 more artefacts, Jason 3, Will and Khargan 1 |  | All
| 2 | Class diagram - discussed OOP principles | Jason has suitable ideas for inheritance, encapsulation, abstraction, polymorphism, interface |  | Jason
3
4
5
6
7
8
9
10
Additional Notes:
Prepared by |  | Kylie