## Agenda
Agenda
Date |  | 2018-09-23 | Time | 2pm | Location |  | Online
To Bring:
Items from previous meeting:
|  | Item |  |  |  | Responsible |  | Due
| 1 | Artefacts - finalise exactly what everyone is doing |  |  |  | All
2
3
4
Items to discuss:
|  | Item |  |  |  | Responsible |  | Due
1
2
3
4
Additional notes:
Prepared by |  | Kylie

## Minutes
Minutes
Participants |  | Will, Jason, Khargan, Kylie, Liam |  | Date |  | 2018-09-23
|  | Items Delivered | Items Planned |  | Impediments
| William | Worked on new release plan | Keep working on release plan |  | spending time with family the whole mid sem break
| Jason | Did class diagram and fixed up Home page button redirecting to forms page. Added a report form button | Keep working on class diagram and website |  | Have urologist appointment tomorrow at 10:10AM so might not make the meeting if the dr takes too long
| Liam | did account settings UI | don't know |  | Australian Tax Office stuff
| Khargan | Honestly not much, been focusing on mobile / applying for summer semester at UQ | Work on login page |  | Cab403 assignment work that's about it
| Kylie | Fixed up minutes/agendas for upload, tidied up the database a bit | Fix UML, do other artefacts if I have time |  | May be pretty short on time to get things done by tomorrow
|  | Item Discussed | Resolution |  | Responsible |  | Due
| 1 | Liam's artefacts | Only has one; discussed finding code for him to do, but Khargan and Jason didn't have an idea; settled on more UI diagrams |  | Liam
| 2 | Khargan's artefacts | Has three; will create login page and one UI design for five |  | Khargan
| 3 | Kylie's artefacts | Has four; will try to link database to website for fifth |  | Kylie
| 4 | Jason's artefacts | Has three; needs to find two more |  | Jason
| 5 | Will's artefacts | Already has five |  | Will
| 6 | UI designs | Khargan recommended Balsamiq for high fidelity wireframe design |  | All
| 7 | Database tables - should Kylie add more to accommodate things not in the given spreadsheets? | Kylie will expand if necessary in sprint 2 |  | Kylie
8
9
10
Additional Notes:
Meeting tomorrow unlikely to happen due to people being unavailable.
Prepared by |  | Kylie